## 1. Data to be published
Project name | ICT Procurement Programme
Department | CPS
MPA RAG rating (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the MPA Annual Report) | Amber
Description / Aims (From GMPP data) | ICT contracts for the department are due to expire in November 2015. This programme is to provide for continuity of operations for ICT services for the CPS beyond Nov 2015. The plan is that the CGI Compass contract will be extended to the end of Mar 2017. The contract will be renegotiated with the Print Services and the Networks and Telephony Services removed from Nov 2015 and Mar 2016 respectively. These services will then be procured through pan-government frameworks (PSN Connectivity, PSN Services and Print Services) prior to removal from the Compass contract. The programme will manage the necessary procurements, contract agreements and service transitions.
Departmental commentary on actions planned or taken on the MPA RAG rating. | The CPS have had a Gateway review since the Q2 GMPP report. Out of this review there were 7 actions assigned the CPS, 4 of which have been completed with the other three being ongoing pieces of work to develop the in-house SIAM capability of the CPS.
Project - Start Date (Latest approved start date) | 2013-10-01
Project - End Date (Latest approved end date) | 2016-03-31
Departmental narrative on schedule, including any deviation from planned schedule (if necessary) | The CPS is confident that the redefined programme structure will deliver to the timescales set out above.
2014/2015 Budget (£million) | £3.00m
2014/2015 Forecast (£million) | £3.00m
2014/2015 Variance (£million) | £0.00m
2014/2015 Variance %age | 0%
Total budgeted whole life costs (£million) (including non-government costs) | £183.98m
Departmental narrative on budget/forecast variance for 2014/15 (if variance is more than 5%) | Budget variance less than 5%
Departmental narrative on budgeted whole life costs | Since this submission, the programme has changed direction, moving away from the tower model with Cabinet Office agreement and with reduced scope for this first tranche of contracts. As a result the whole life costs of the programme is now to £85.28m with forecast savings of 21% against like-for-like ICT run costs.